## Munkalap1
Test ID | Kind | Type | Module | Precondition | Testcase | Description | Date of last successful run | Expected result | Actual result | Latest result | Tester
1 | Manual | Acceptance | Authentication | The user already has a registered account | User log in with the data of their account | I entered the email and the password the clicked on the Log In button | 2026-01-07 | Passed | Passed | Passed | G.M
2 | Manual | Unit | Functional | The user can choose regular haircut | User tried to pick the regular haircut option | I picked the regular haircut option when I booked an appointment | 2026-01-08 | Passed | Passed | Passed | G.M
3 | Manual | Unit | Functional | The user can choose perfect haircut | User tried to pick the perfect haircut option | I picked the perfect haircut option when I booked an appointment | 2026-01-08 | Passed | Passed | Passed | G.M
4 | Manual | Unit | Functional | The user can choose beard trim | User tried to pick the beard trim option | I picked the beard trim option when I booked an appointment | 2026-01-08 | Passed | Passed | Passed | G. M
5 | Manual | Unit | Functional | The user can choose fullbox | User tried to pick the fullbox option | I picked the fullbox option when I booked an appointment | 2026-01-08 | Passed | Passed | Passed | G. M
6 | Manual | Unit | Functional | The user can choose Blowout Ben | User tried to pick the Blowout Ben as a barber | I picked Blowout Ben as my barber | 2026-01-08 | Passed | Passed | Passed | G. M
7 | Manual | Unit | Functional | The user can choose Crispy Chris | User tried to pick the Crispy Chris as a barber | I picked Crispy Chris as my barber | 2026-01-08 | Passed | Passed | Passed | G. M
8 | Manual | Unit | Functional | The user can choose Haircut Harry | User tried to pick the Haircut Harry as a barber | I picked Haircut Harry as my barber | 2026-01-08 | Passed | Passed | Passed | G. M
9 | Manual | Unit | Functional | The user can choose Bouncy Bella | User tried to pick the Bouncy Bella as a barber | I picked Bouncy Bella as my barber | 2026-01-08 | Passed | Passed | Passed | G. M
10 | Manual | Unit | Functional | The user can choose Loud Lucy | User tried to pick the Loud Lucy as a barber | I picked Loud Lucy as my barber | 2026-01-08 | Passed | Passed | Passed | G. M
11 | Manual | Unit | Functional | The user can choose a date | User tried to choose a date for the appointment | I picked a free time slot for an appointment | 2026-01-08 | Passed | Passed | Passed | G. M
12 | Manual | Unit | Functional | The user can't choose a reserved date | User tried to choose a reserved date for the appointment | I picked tried to pick reserved time slot for an appointment | 2026-01-08 | Passed | Passed | Passed | G. M
13 | Automated | Acceptance | Navigation | The webiste is running | Frontend pages are reachable via direct url | I opened the pages via direct urls with selenium tests | 2026-01-08 | Passed | Passed | Passed | G. M
14 | Automated | Acceptance | Authentication | The user is not signed in | Sign up modal opens from auth choice screen | Verifies that clicking the sign-up button from the authentication choice screen opens the sign-up modal. | 2026-01-08 | Passed | Passed | Passed | RB
15 | Automated | Acceptance | Authentication | The user doesn't have a registered account | Successful sign up redirects user to booking page | Verifies that a user can successfully sign up with valid data and is redirected to the booking page. | 2026-01-08 | Passed | Passed | Passed | RB
16 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails due to invalid password format | Verifies that sign-up fails when the password does not meet security requirements and an error message is shown. | 2026-01-08 | Passed | Passed | Passed | RB
17 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails when password and confirm password do not match | Verifies that sign-up fails if the password and confirmation password do not match. | 2026-01-08 | Passed | Passed | Passed | RB
18 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails with invalid email address | Verifies that sign-up fails when an invalid email address is provided. | 2026-01-08 | Passed | Passed | Passed | RB
19 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails due to invalid first name | Verifies that sign-up fails when the first name does not meet validation rules. | 2026-01-08 | Passed | Passed | Passed | RB
20 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails due to invalid last name | Verifies that sign-up fails when the last name does not meet validation rules. | 2026-01-08 | Passed | Passed | Passed | RB
21 | Automated | Acceptance | Authentication | The user is not signed in | Sign up fails when password and confirm password do not match | Verifies that sign-up fails if the password and confirmation password do not match. | 2026-01-08 | Passed | Passed | Passed | RB
22 | Automated | Acceptance | Authentication | The user is not signed in | Book Now shows authentication choice modal for guest users | Verifies that clicking the Book Now button while not logged in displays the authentication choice modal. | 2026-01-08 | Passed | Passed | Passed | RB
23 | Automated | Acceptance | Authentication | The user is not signed in | Header sign-in button opens authentication choice modal | Verifies that clicking the sign-in button in the header opens the authentication choice modal. | 2026-01-08 | Passed | Passed | Passed | RB
24 | Automated | Acceptance | Authentication | The user is not signed in | Guest user can continue to booking page | Verifies that a guest user can continue to the booking page without signing in. | 2026-01-08 | Passed | Passed | Passed | RB
25 | Manual | Unit | Appointment Management | Backend is running | Get available time slots for a given day | The system returns available time slots for the selected day | 2026-01-08 | Passed | Passed | Passed | TB
26 | Manual | Unit | Appointment Management | Backend is running | Do not return already booked time slots | The system does not return time slots that are already booked | 2026-01-08 | Passed | Passed | Passed | TB
27 | Manual | Unit | Appointment Management | Backend is running | Do not return past time slots | The system does not return time slots in the past | 2026-01-08 | Passed | Passed | Passed | TB
28 | Manual | Unit | Appointment Management | Backend is running | Book a time slot successfully | A time slot can be booked with valid parameters | 2026-01-08 | Passed | Passed | Passed | TB
29 | Manual | Unit | Appointment Management | Backend is running | Cannot book a time slot in the past | Booking a time slot in the past is not allowed | 2026-01-08 | Passed | Passed | Passed | TB
30 | Manual | Unit | Appointment Management | Backend is running | Cannot book an already booked interval | Booking an already reserved time interval is not allowed | 2026-01-08 | Passed | Passed | Passed | TB
31 | Manual | Unit | Appointment Management | Backend is running | Cannot book without required parameters | Booking fails if required parameters are missing | 2026-01-08 | Passed | Passed | Passed | TB
32 | Manual | Unit | Services managment | Backend is running | Get all services | The system returns all available services | 2026-01-08 | Passed | Passed | Passed | TB
33 | Manual | Unit | Employee managment | Backend is running | Get all employees without service filter | The system returns all employees when no service is specified | 2026-01-08 | Passed | Passed | Passed | TB
34 | Manual | Unit | Employee managment | Backend is running | Get relevant employees for a service | The system returns only employees relevant to the selected service | 2026-01-08 | Passed | Passed | Passed | TB
35 | Automated | Acceptance | Authentication | The user is not signed in | Sign in from auth choice opens login modal | Verifies that selecting sign-in from the authentication choice screen opens the login modal. | 2026-01-08 | Passed | Passed | Passed | RB
36 | Automated | Acceptance | Authentication | The user has already created an account | Successful login redirects user to booking page | Verifies that a user can successfully sign in with valid credentials and is redirected to the booking page. | 2026-01-08 | Passed | Passed | Passed | RB
37 | Automated | Acceptance | Authentication | Valid login credentials | Header sign-in shows success notification | Verifies that signing in from the header displays a success notification. | 2026-01-08 | Passed | Passed | Passed | RB
38 | Automated | Acceptance | Authentication | The user already has logged in | Signed-in user can navigate to booking page | Verifies that a signed-in user can access the booking page using the Book Now button. | 2026-01-08 | Passed | Passed | Passed | RB
39 | Automated | Acceptance | Authentication | The user is not signed in | Sign in fails with invalid email format | Verifies that sign-in fails when the email format is invalid and an error message is shown. | 2026-01-08 | Passed | Passed | Passed | RB
40 | Automated | Acceptance | Authentication | The user is not signed in | Sign in fails with incorrect credentials | Verifies that sign-in fails when incorrect credentials are provided. | 2026-01-08 | Passed | Passed | Passed | RB
41 | Automated | Acceptance | Authentication | The user is not signed in | Sign in fails when required fields are empty | Verifies that sign-in fails when submitting the form with empty required fields. | 2026-01-08 | Passed | Passed | Passed | RB
42 | Automated | Acceptance | Authentication | The user is not signed in | Sign in fails when password field is empty | Verifies that sign-in fails when the password field is not provided. | 2026-01-08 | Passed | Passed | Passed | RB
43 | Manual | Unit | Functional | The user must have continued as a guest | As a guest personal data is required | Verifies if the user starts the booking as a guest, they must enter their personal information in the last section | 2026-01-08 | Passed | Passed | Passed | RB
44 | Manual | Unit | Functional | The user has to be on the booking page | Must complete every booking step | Verifies that the user is not able to skip sections in the booking form, every section is required for a successfull booking | 2026-01-08 | Passed | Passed | Passed | RB
45 | Manual | Unit | Functional | The user has already signed in | As a signed in user only 3 sections shows up in the booking form | Verifies that a logged in user has to complete only 3 sections in the booking form | 2026-01-08 | Passed | Passed | Passed | RB
46 | Manual | Unit | Functional | The user must complete the first 2 steps | 30 mins long service will reserve 1 time slot | Verifies that a 60mins service reserves 1 time slots | 2026-01-08 | Passed | Passed | Passed | RB
46 | Manual | Unit | Functional | The user must complete the first 2 steps | 60 mins long service will reserve 2 time slots | Verifies that a 60mins service reserves 2 time slots | 2026-01-08 | Passed | Passed | Passed | RB
47 | Automated | Acceptance | Booking | Registered customer exists | Logged-in user can complete booking flow | Cypress opens /booking, selects service, barber, slot, submits booking as signed-in user, verifies redirect to confirmation-pending and validates request payload. | 2026-04-28 | Passed | Passed | Passed | RB
48 | Automated | Acceptance | Booking | Guest user (no login) | Guest can complete booking flow | Cypress opens /booking, selects service, barber, slot, enters guest name/email, submits booking, verifies redirect and payload includes guest fields. | 2026-04-28 | Passed | Passed | Passed | RB
49 | Automated | Acceptance | Booking | Guest user, invalid guest email case | Booking API validation error is shown for guest email | Cypress mocks 422 response for /appointments (guest_email validation error), submits booking as guest, checks visible error message and no redirect. | 2026-04-28 | Passed | Passed | Passed | RB
50 | Manual | Acceptance | Public Pages | Frontend is available | Home page displays main sections | Open the home page and verify that hero, services, barbers, gallery and booking call-to-action are visible. | 2026-04-28 | Passed | Passed | Passed | G.M
51 | Manual | Acceptance | Public Pages | Services are seeded in the database | Services list is visible on the public page | Open the services section and verify that the barber services are loaded from the system. | 2026-04-28 | Passed | Passed | Passed | G.M
52 | Manual | Acceptance | Public Pages | Employees are seeded in the database | Barbers page lists available barbers | Open /barbers and verify that the demo barbers appear with photo, name, bio and booking option. | 2026-04-28 | Passed | Passed | Passed | G.M
53 | Manual | Functional | Public Pages | A barber is visible on the Barbers page | Barber profile page opens correctly | Open a barber profile and verify the profile details, services, gallery and reviews are displayed. | 2026-04-28 | Passed | Passed | Passed | G.M
54 | Manual | Acceptance | Public Pages | Shop information exists | Contact page displays shop information | Open /contact and verify address, phone, email, opening hours, links and map are shown. | 2026-04-28 | Passed | Passed | Passed | G.M
55 | Manual | Acceptance | Authentication | The user is not registered yet | Customer can register with valid data | Open Sign Up, enter valid name, email and strong password, then submit the form. | 2026-04-28 | Passed | Passed | Passed | G.M
56 | Manual | Functional | Authentication | The user is on the Sign Up form | Weak password is rejected during registration | Enter a password that does not meet the requirements and verify that the form shows validation feedback. | 2026-04-28 | Passed | Passed | Passed | G.M
57 | Manual | Acceptance | Authentication | A verification email was generated | Customer can verify email address | Open the verification link from Mailcatcher and verify that the email address becomes verified. | 2026-04-28 | Passed | Passed | Passed | G.M
58 | Manual | Acceptance | Authentication | The customer has a verified account | Customer can sign in with valid credentials | Open Sign In, enter valid customer email and password, then verify that the user is logged in. | 2026-04-28 | Passed | Passed | Passed | G.M
59 | Manual | Functional | Authentication | The user is not signed in | Invalid login credentials are rejected | Enter an existing email with a wrong password and verify that access is denied. | 2026-04-28 | Passed | Passed | Passed | G.M
60 | Manual | Acceptance | Authentication | The customer has an account | Password reset email can be requested | Open Forgot password, enter the account email and verify that the reset email is generated. | 2026-04-28 | Passed | Passed | Passed | G.M
61 | Manual | Acceptance | Booking | The booking page is open | Guest can start booking flow | Continue as guest and verify that the booking form can be opened without signing in. | 2026-04-28 | Passed | Passed | Passed | G.M
62 | Manual | Functional | Booking | At least one service is available | User can select multiple services | Select more than one service and verify that the selection remains visible in the booking flow. | 2026-04-28 | Passed | Passed | Passed | G.M
63 | Manual | Functional | Booking | Services are selected | Only suitable barbers are listed | After selecting services, verify that only barbers assigned to those services are displayed. | 2026-04-28 | Passed | Passed | Passed | G.M
64 | Manual | Acceptance | Booking | Service and barber are selected | User can choose a free date and time slot | Select a bookable day and one available time slot from the calendar. | 2026-04-28 | Passed | Passed | Passed | G.M
65 | Manual | Functional | Booking | Multiple services and a slot are selected | Booking summary calculates total duration and price | Verify that the summary shows the selected services and the correct combined duration and price. | 2026-04-28 | Passed | Passed | Passed | G.M
66 | Manual | Acceptance | Booking | Guest data is available and a free slot is selected | Guest booking creates a pending appointment | Submit the booking as guest and verify that the confirmation pending page is shown. | 2026-04-28 | Passed | Passed | Passed | G.M
67 | Manual | Acceptance | Booking | A pending booking confirmation email exists | Booking can be confirmed by email link | Open the confirmation link from Mailcatcher and verify that the booking summary page appears. | 2026-04-28 | Passed | Passed | Passed | G.M
68 | Manual | Acceptance | Booking | The customer is signed in | Signed-in customer can book without guest fields | Complete a booking while signed in and verify that guest name and guest email are not required. | 2026-04-28 | Passed | Passed | Passed | G.M
69 | Manual | Functional | Booking | The booking calendar is visible | Past dates cannot be selected | Check the calendar and verify that dates before the current day are not bookable. | 2026-04-28 | Passed | Passed | Passed | G.M
70 | Manual | Functional | Booking | A time slot is already booked | Occupied time slot is not offered again | Create or use an existing booking and verify that the same barber and time slot is no longer available. | 2026-04-28 | Passed | Passed | Passed | G.M
71 | Manual | Functional | Booking | Guest booking is being submitted | Registered email cannot be used for guest booking | Try to book as guest with an email that belongs to a registered user and verify that validation blocks the booking. | 2026-04-28 | Passed | Passed | Passed | G.M
72 | Manual | Acceptance | Customer | The customer is signed in | Customer can view own appointments | Open Your Appointments and verify that the customer appointments are listed with service, barber, date, price and status. | 2026-04-28 | Passed | Passed | Passed | G.M
73 | Manual | Acceptance | Customer | The customer has a pending or confirmed appointment | Customer can cancel an active appointment | Cancel an active appointment and verify that its status changes to cancelled. | 2026-04-28 | Passed | Passed | Passed | G.M
74 | Manual | Acceptance | Customer | The customer has a completed appointment without review | Customer can leave a review | Open the review modal, select a completed appointment, enter rating and comment, then submit it. | 2026-04-28 | Passed | Passed | Passed | G.M
75 | Manual | Functional | Customer | The appointment already has a review | Customer cannot review the same appointment twice | Try to submit another review for the same appointment and verify that the system prevents it. | 2026-04-28 | Passed | Passed | Passed | G.M
76 | Manual | Acceptance | Employee | Employee credentials are available | Employee can sign in | Open /employee/login, enter employee credentials and verify that the employee dashboard is accessible. | 2026-04-28 | Passed | Passed | Passed | G.M
77 | Manual | Acceptance | Employee | The employee is signed in | Employee can view own appointments | Open the employee appointments page and verify that only appointments assigned to the employee are shown. | 2026-04-28 | Passed | Passed | Passed | G.M
78 | Manual | Functional | Employee | The employee has a future appointment | Employee can cancel an appointment with reason | Cancel a future appointment, enter a cancellation reason and verify the appointment becomes cancelled. | 2026-04-28 | Passed | Passed | Passed | G.M
79 | Manual | Functional | Employee | The employee has a past confirmed appointment | Employee can mark appointment as completed | Mark a past confirmed appointment as completed and verify that the status is updated. | 2026-04-28 | Passed | Passed | Passed | G.M
80 | Manual | Functional | Employee | The employee has a past confirmed appointment | Employee can mark appointment as no-show | Mark a past confirmed appointment as no-show and verify that the status is updated. | 2026-04-28 | Passed | Passed | Passed | G.M
81 | Manual | Acceptance | Employee | The employee is signed in | Employee can request time off | Open Time Off, add a day and reason, submit the request and verify it appears as pending. | 2026-04-28 | Passed | Passed | Passed | G.M
82 | Manual | Acceptance | Admin | Admin credentials are available | Admin can sign in | Open /admin/login, enter admin credentials and verify that the admin area is accessible. | 2026-04-28 | Passed | Passed | Passed | G.M
83 | Manual | Acceptance | Admin | The admin is signed in | Admin can filter appointments | Open Appointments, filter by status, employee or service and verify that the list changes accordingly. | 2026-04-28 | Passed | Passed | Passed | G.M
84 | Manual | Functional | Admin | The admin is signed in | Admin can create a new service | Open Services, add a new service and verify that it appears in the service list. | 2026-04-28 | Passed | Passed | Passed | G.M
85 | Manual | Functional | Admin | The admin is signed in and employees exist | Admin can configure employee services | Open an employee configuration, change assigned services, price or duration and save the changes. | 2026-04-28 | Passed | Passed | Passed | G.M
86 | Manual | Functional | Admin | The admin is signed in | Admin can edit shop opening hours | Open Schedule, change a weekly opening hour and verify that the change is saved. | 2026-04-28 | Passed | Passed | Passed | G.M
87 | Manual | Functional | Admin | The admin is signed in | Admin can add a special closed day | Open Schedule, add a special closed day and verify it appears in the calendar. | 2026-04-28 | Passed | Passed | Passed | G.M
88 | Manual | Acceptance | Admin | A pending time off request exists | Admin can approve time off request | Open Time Off, approve a pending request and verify that the status changes to approved. | 2026-04-28 | Passed | Passed | Passed | G.M
89 | Manual | Functional | Admin | Reviews exist in the system | Admin can change review visibility | Open Reviews, toggle a review visibility and verify that the saved state is updated. | 2026-04-28 | Passed | Passed | Passed | G.M
90 | Manual | Acceptance | Admin | The admin is signed in | Admin can update shop profile | Open Shop Profile, update contact details or gallery image and verify the public data is changed. | 2026-04-28 | Passed | Passed | Passed | G.M
91 | Automated | Feature | Backend Booking API | Bookable employee and services exist | Booking routes return services, employees, days and slots | Covers /api/booking/services, employees, summary, days and slots responses for a valid booking setup. | 2026-04-28 | Passed | Passed | Passed | RB
92 | Automated | Feature | Backend Customer Appointments | Customer has own and other customer appointments | Customer only sees and cancels own appointments | Verifies user appointment listing, forbidden cancellation of another customer appointment and own cancellation status update. | 2026-04-28 | Passed | Passed | Passed | RB
93 | Automated | Feature | Backend Booking API | Logged-in customer has a valid API token | Logged-in customer can book without guest details | Creates an appointment using bearer token authentication and verifies the booking is saved as pending for the customer. | 2026-04-28 | Passed | Passed | Passed | RB
94 | Automated | Feature | Backend Booking API | Invalid bearer token is provided | Invalid bearer token cannot book as guest by accident | Verifies that an invalid Authorization bearer token returns unauthenticated instead of silently creating a guest booking. | 2026-04-28 | Passed | Passed | Passed | RB
95 | Automated | Feature | Backend Booking API | Expired bearer token is provided | Expired bearer token cannot book as guest by accident | Verifies that an expired API token returns unauthenticated and does not create a guest booking. | 2026-04-28 | Passed | Passed | Passed | RB
96 | Automated | Feature | Backend Booking Confirmation | A pending appointment and signed confirmation URL exist | Confirmation changes pending appointment to confirmed once | Verifies the confirmation endpoint updates status to confirmed, sends summary email and rejects a repeated confirmation. | 2026-04-28 | Passed | Passed | Passed | RB
97 | Automated | Feature | Backend Employee Appointments | Employee owns a confirmed appointment | Employee can complete own confirmed appointment | Verifies the employee endpoint can mark an owned confirmed appointment as completed. | 2026-04-28 | Passed | Passed | Passed | RB
98 | Automated | Feature | Backend Booking Limit | Customer already has an active appointment in the same week | Authenticated user can book multiple active appointments in same calendar week | Verifies that authenticated customers are allowed to create another active booking in the same calendar week. | 2026-04-28 | Passed | Passed | Passed | RB
99 | Automated | Feature | Backend Booking Limit | Guest email already has an active appointment in the same week | Guest can book multiple active appointments in same calendar week | Verifies that a guest can create another active appointment using the same guest email in the same week. | 2026-04-28 | Passed | Passed | Passed | RB
100 | Automated | Feature | Backend Booking Limit | Customer has a cancelled appointment in the same week | Cancelled appointments do not block new booking | Verifies that cancelled appointments do not prevent creating another appointment in the same calendar week. | 2026-04-28 | Passed | Passed | Passed | RB
101 | Automated | Feature | Backend Booking Limit | Customer has a completed appointment in the same week | Completed appointments do not block new booking | Verifies that completed appointments do not prevent creating another appointment in the same calendar week. | 2026-04-28 | Passed | Passed | Passed | RB
102 | Automated | Feature | Backend Booking Limit | Customer has an appointment in another week | Customer can book again in a different calendar week | Verifies that a customer can create a booking in a different week when an older pending booking exists. | 2026-04-28 | Passed | Passed | Passed | RB
103 | Automated | Feature | Backend Employee Cancel | Employee owns an upcoming confirmed appointment | Barber can cancel own appointment with valid reason | Verifies employee cancellation with reason, cancelled status persistence and cancellation email sending. | 2026-04-28 | Passed | Passed | Passed | RB
104 | Automated | Feature | Backend Employee Cancel | Employee owns an upcoming pending appointment | Barber cancel requires cancellation reason | Verifies missing cancellation reason returns validation error and valid reason allows cancellation. | 2026-04-28 | Passed | Passed | Passed | RB
105 | Automated | Feature | Backend Employee Cancel | Employee owns a past confirmed appointment | Barber cancel past appointment still requires reason | Verifies past appointment cancellation without reason is rejected and no mail is sent. | 2026-04-28 | Passed | Passed | Passed | TB
106 | Automated | Feature | Backend Employee Cancel | Appointment belongs to another employee | Barber cannot cancel another barber appointment | Verifies employee cannot cancel appointments assigned to a different barber. | 2026-04-28 | Passed | Passed | Passed | TB
107 | Automated | Feature | Backend Employee Cancel | Appointment is already cancelled | Barber cannot cancel already cancelled appointment | Verifies repeated cancellation is rejected and the original cancellation reason remains unchanged. | 2026-04-28 | Passed | Passed | Passed | TB
108 | Automated | Feature | Backend Email Verification | User is unverified and has valid signed verification URL | Verification endpoint marks user as verified | Verifies the email verification endpoint marks the user verified and returns success status. | 2026-04-28 | Passed | Passed | Passed | TB
109 | Automated | Feature | Backend Email Verification | User is already verified | Verification endpoint reports already verified users | Verifies the endpoint returns already_verified for a user whose email is already confirmed. | 2026-04-28 | Passed | Passed | Passed | TB
110 | Automated | Feature | Backend Email Verification | Expired verification URL exists | Verification endpoint rejects expired links | Verifies expired signed verification links return invalid status and do not verify the user. | 2026-04-28 | Passed | Passed | Passed | TB
111 | Automated | Feature | Backend Registration | Notification fake is active | Registration sends custom verification notification | Verifies registration creates a user and sends the custom VerifyEmailNotification. | 2026-04-28 | Passed | Passed | Passed | TB
112 | Automated | Feature | Backend Authentication | Verified customer exists | Verified customer can log in and receives serialized verification timestamp | Verifies customer login response, token creation and serialized email verification timestamp. | 2026-04-28 | Passed | Passed | Passed | TB
113 | Automated | Feature | Backend Authentication | Verified employee exists | Verified employee can log in and receives serialized verification timestamp | Verifies employee login response, token creation and serialized email verification timestamp. | 2026-04-28 | Passed | Passed | Passed | TB
114 | Automated | Feature | Backend Authentication | Unverified customer exists | Unverified user cannot log in and receives verification message | Verifies unverified login is blocked and a new verification notification is sent. | 2026-04-28 | Passed | Passed | Passed | TB
115 | Automated | Feature | Backend Authentication | User has an active API token | Logout revokes the current API token | Verifies logout returns success and removes the current token hash from the database. | 2026-04-28 | Passed | Passed | Passed | TB
116 | Automated | Feature | Backend Authentication | User can receive API tokens | Only one active API token is kept per user | Verifies issuing a second API token removes the previous one and keeps only the latest token. | 2026-04-28 | Passed | Passed | Passed | TB
117 | Automated | Feature | Backend Employee Data | Employee has appointment with service and customer | Barber appointments endpoint returns service and client names | Verifies employee appointments response contains client name, service name, status and start datetime. | 2026-04-28 | Passed | Passed | Passed | TB
118 | Automated | Feature | Backend Employee Profile | Employee profile image and gallery image exist | Barber profile endpoint returns employee name and image URLs | Verifies employee profile response contains name, description, profile image URL and gallery preview URL. | 2026-04-28 | Passed | Passed | Passed | TB
119 | Automated | Feature | Backend Employee Profile | Employee is authenticated | Barber profile update persists employee name and description | Verifies PATCH /api/employee/profile updates the employee name and bio. | 2026-04-28 | Passed | Passed | Passed | TB
120 | Automated | Feature | Backend Employee Reviews | Completed appointment has a review | Barber reviews endpoint returns customer names | Verifies employee reviews response contains client name, rating and comment. | 2026-04-28 | Passed | Passed | Passed | TB
121 | Automated | Unit | Backend Unit | PHPUnit unit test suite is available | Basic unit test asserts true is true | Verifies the example unit test executes a basic true assertion successfully. | 2026-04-28 | Passed | Passed | Passed | TB